PRT Process Checklist for Client CEOs and Point Persons

October 2025

Action items are in rough chronological order, with specific timing triggers identified to the right.

Unless otherwise noted, CEO (or designee, typically one of the point persons) takes actions listed.

See the Typical Process document for more details.

|  | Action | Timing |
| --- | --- | --- |
|  | Submit LOI, which identifies Areas of Focus (AoFs) for technical assistance | Rolling basis; cycle deadlines vary |
| Prior to Visit 1 |  |  |
|  | Schedule initial phone meeting with IEPI Project Director (Peggy Lomas) | Upon email request from Peggy |
|  | Review Peggy’s email for meeting topics, along with attached documents | For phone meeting with Peggy |
|  | Identify 3+ date options for Visit 1; identify 3+ date options for Visit 2 | For phone meeting with Peggy |
|  | Identify additional Areas of Focus not included in Letter of Interest, if any | For phone meeting with Peggy |
|  | Designate a substantive Point Person and logistical Point Person (PPs) | For phone meeting with Peggy |
|  | Conduct initial phone meeting with Peggy | As scheduled |
|  | Share any concerns about potential PRT members with Peggy | After receiving list of PRT members |
|  | Review request for more detailed Commentary on AoFs | Upon receiving request email |
|  | PPs review information request email from Peggy and start gathering info | Upon receiving request email |
|  | Designate Drafting Group(s), which will begin drafting Innovation & Effectiveness Plan (I&EP) during Visit 2 | Before preparing draft Visit 1 schedule |
|  | Develop list of Visit 1 participants (names, titles, committee affiliations) and draft schedule for the day and send both to Peggy | By requested deadline |
|  | PPs send PRT accommodations, parking, and other logistics info to Peggy | By requested deadline |
|  | PPs send crucial documents/links to Peggy | By requested deadline |
|  | Prepare 2-page Commentary on AoFs in consultation with Academic Senate President and send to Peggy | By requested deadline |
|  | PPs share LOI and final AoF Treatment with Visit 1 participants | Before Visit 1 |
|  | CEO and/or PPs inform visit participants and wider college community about nature and purpose of PRT visits | Before Visit 1 |
|  | Phone meeting with Lead to discuss Visit 1 purpose and expectations | Before Visit 1 |
|  | PPs send additional information to PRT, if requested | Upon request |
| During Visit 1 |  |  |
|  | PPs monitor visit logistics to ensure visit proceeds smoothly | During Visit 1 |
|  | Meet with PRT or PRT Lead as scheduled | Beginning and end of Visit 1 |
|  | CEO and PPs participate in other meetings as appropriate | As scheduled |
|  | Set Visit 2 date with PRT Lead (if not already set) | During the day/via email afterwards |
| After Visit 1 / Before Visit 2 |  |  |
|  | CEO, PPs, and others significantly involved in visit respond to PRT process online evaluation | Within 1 week of Visit 1 |
|  | PPs send invoice for cost of any PRT meals to Catherine Crossland, IEPI Program Specialist | After Visit 1 |
|  | Review and distribute SIV as appropriate | Upon receipt of SIV |
|  | PPs send draft schedule for visit and list of I&EP Drafting Group members to Lead | Two weeks before Visit 2 |
|  | Review MOO, suggest any tweaks to the Lead, and distribute the final MOO to I&EP Drafting Group | Upon receipt of MOO |
|  | I&EP Drafting Group members reflect on and discuss MOO to prepare for Visit 2 | During week before Visit 2 |
|  | Phone meeting with Lead to discuss Visit 2 | Before Visit 2 |
|  | Confirm structure and schedule of Visit 2 with Lead | Before Visit 2 |
|  | PPs send additional information to PRT, if requested | Upon request |
|  | PPs check with Lead to finalize visit preparations as needed | Before Visit 2 |
| During Visit 2 |  |  |
|  | PPs monitor visit logistics to ensure visit proceeds smoothly | During Visit 2 |
|  | Meet with PRT or PRT Lead as scheduled | Beginning and/or end of Visit 2 |
|  | I&EP Drafting Group meets with PRT to discuss MOO and begin drafting I&EP | As scheduled |
|  | CEO and/or PPs participate in Drafting Group meeting if needed | As scheduled |
| After Visit 2 / Before Visit 3 |  |  |
|  | CEO, PPs, and others significantly involved in visit respond to PRT process online evaluation | Within 1 week of Visit 2 |
|  | PPs send invoice for cost of any PRT meals to Catherine, IEPI Program Specialist | After Visit 2 |
|  | Read the “Next Steps in the PRT Process” email from Peggy | Upon receipt of email |
|  | Ensure I&EP Drafting Group completes the I&EP draft | By requested deadline |
|  | Send I&EP draft to Peggy and PRT Lead for feedback | About 1 week after Visit 2 |
|  | Review and incorporate feedback into final I&EP; Academic Senate President(s) sign(s) the I&EP (signifying that collegial consultation with the Senate or its President has occurred); CEO signs it and emails it to Peggy and Lead | Within 1 week after receiving feedback |
|  | Begin implementing aspects of I&EP that do not require Seed Grant funding | After submitting final I&EP |
|  | Complete Seed Grant forms, sign, and email to Santa Clarita CCD, with copy to Peggy | 1 week after receipt of forms |
|  | PPs send Peggy and PRT Lead three potential Visit 3 date options | Upon request, after submitting final I&EP and Seed Grant forms |
|  | Institution commences implementation of entire I&EP | Upon receiving Grant check |
|  | Initiate preparation of implementation status report upon receipt of email request | 4 weeks before Visit 3 |
|  | Invite individuals and/or groups who are in the best position to report on progress or wish to request implementation guidance from the PRT to participate in Visit 3 | Before Visit 3 |
|  | PPs send draft schedule for visit and list of participants to Lead | One week before Visit 3 |
|  | Phone meeting with Lead to discuss Visit 3; request end-of-visit meeting with PRT if desired; agree on final agenda and list of participants; send final agenda and list to Peggy and Lead | Before Visit 3 |
|  | PPs send status report on I&EP implementation to Peggy | 2 weeks before Visit 3 |
|  | PPs check with Lead to finalize visit preparations as needed | Before Visit 3 |
| During Visit 3 |  |  |
|  | PPs monitor visit logistics to ensure visit proceeds smoothly | During Visit 3 |
|  | Meet with PRT or PRT Lead | Beginning of Visit 3 |
|  | Institutional personnel meet with PRT to discuss progress, request advice on I&EP implementation and sustaining progress, discuss whether additional visit(s) would be helpful to the institution, and (unless further visits are requested) come to closure on the visit’s component of the PRT process | During Visit 3 |
|  | If desired, meet with PRT or PRT Lead | End of Visit 3 |
| After Visit 3 |  |  |
|  | CEO, PPs, and others significantly involved in visit respond to PRT process online evaluation | Within 1 week of Visit 3 |
|  | PPs send invoice for cost of any PRT meals to IEPI Program Specialist | After Visit 3 |
|  | Review PRT Process Summary Report | Upon receipt of report |
|  | Provide information on institutional improvements related to PRT process | Upon request from Peggy |
|  | Participate in initial evaluation of longer-term effects of PRT process | 10-12 months after Visit 3 |
|  | Participate in later evaluations of longer-term effects of PRT process | Annually thereafter |

IEPI Contacts

Peggy Lomas., IEPI Project Director: peggy.lomas@canyons.edu

Catherine Crossland, IEPI Program Specialist II: catherine.crossland@canyons.edu

Diane Rausch, IEPI Administrative Coordinator: diane.rausch@canyons.edu